## Oceano
Task | Status | Requirement | Category | Priority | Assigned To | Assigned Date | Deadline Date | Status | Remarks | Last Update Date
Vehicle Branding | Delayed | Hiace vehicle sticker has faded and they need a revised version that includes all the newly added SKUs. | Offline | Medium | Outsourcing | 2026-04-16 |  | OnHold | Taken quotation from agencies & submitted, It's currently on hold. Upto next renewal time (2027 Jan) | 2026-07-04
Second Branding Name | In Review | They required a 2nd brand name that will have 'N' numbers of product category | New Brand | Medium | Agency (Innox future) | 2026-05-13 |  | In Progress | Initially we given 9 options derived by Abedhad, that was not ok for oceano. We outsouced it. Parallelly i takenotes from agencies for complete branding. | 2026-07-07
Burger Sleeve | Concept Progress | Oceano require a burger sleeve design with the same shape and dimensions as the Cooked Shrimp 300g sleeve. | Packaging RTC | Medium | Amal | 2026-06-06 | 2026-07-13 | Oceano will update the Print format & revert. | Last option shared with oceano | 2026-07-07
Hamour Sleeve |  | Adaptation of Hamour Fillet - product img to be changed rest all the contents remain same | Packaging RTC | High | Navas | 2026-06-13 | 2026-07-13 | Oceano will update the Print format & revert. | We shared the options as per the oceano requirement | 2026-07-02
Bus Ads |  | Marketing Team suggested the campaign to oceano. 1 (One) Ajman to Dubai Bus and 5 Taxi's Branding slot for the month of September on the Ajman–Dubai route. Digital Screens - 3 screens total - 2 screen @ lulu junction, 1 Screen at Univeristy street @ Ajman for one month (30 days). | Offline | Medium | Agency (Bangalore team) Amal | 2026-05-19 | 2026-07-27 | In Progress | We outsourced initially with an agency called Elevage. That didn't work well. After we associate with a bangalore base agency, they submit options and oceano was ok to proceed this options. But edits were there.Now the Bus Ad time extends, we are waiting for bangalore agency to share new option, That will be submitted before July 15th. | 2026-07-03
1+1 Smoked Salmon |  | Oceano 1+1 Smoked Salmon is not attention-grabbing, due to which comparatively we have lesser sales. The attention does not go to Oceano 1+1, so kindly, keeping the premium factor in mind, update/Redesign on how we can make the Oceano 1+1 Smoked Salmon more eye-catching. | Print | Medium | Amal | 2026-06-17 |  | Waiting from Oceano end
Website Content Validation |  | Oceano required to change the currect content to better fluentcy. | Website | High | Abedhab - Agency in kochi |  | 2026-07-07 | Content Shared | We have done multiple options taken through agency and internally. Last agency option is approved by Mr. Noufal. The revised option shared. | 2026-07-07
Social Media (Posters) |  |  | Social Media | Daily Task
Grandiose Smoked Salmon |  | Oceano will be proceeding with the private labeling of Grandiose Smoked Salmon products. Accordingly, we require the back side content for the smoked salmon pouches | Print |  | Navas | 2026-06-27 | 2026-07-08 | Waiting from Oceano end | We have done the requirement. Edits given. Need to share ASAP | 2026-07-07
Keeta Launch |  | They didn't mention any requirement, only update to us that, will be launching our online restaurant delivery service on the Keeta platform on Friday, 17th July. |  | Medium |  | 2026-07-01 | Launch on 17-Jul-2026 |  | They give us the permission to do activities, but inform the before conducting anything. | 2026-07-07
New Product Launch - Photos & Videos |  | Their marination items and cleaned and cut items are all set and will be pushed to the market shortly They required the same is reflected in social media as launching video like how they have been doing for our launching video for other products. | Launch | High | Sharikh | 2026-06-26 |  |  | This we need to take product shoot & website photos to proceed. Sharikh is helpless to edit with stock footages. | 2026-07-06
Tobiko sticker |  | They design is over, issue facing while printing. Need to rework this. | Packaging | Medium | Amal | 2026-01-01 |  | Hold | Need to consult with agency.
ONLINE Platforms - Careem, Noon & Amazon |  | Currently we are not doing any promotions | Digital | High | Abedhab | 2026-01-01 |  | In Progress | Because off season, campaigns hold for amazon. Noon we are following up. Craeem need to take decision. | 2026-07-06
Ai Images - for Kibsons |  | Remaining products | Digital | High | Amal |  | 10.07.26
1. OceanoXDeep - PPT 2. Oceano PPT Image changes |  | All products (other than sushi range)- img to be changed Marination items corrections which is marked in the group to be corrected | Digital | Medium | Amal | 09.07.26 | 14.07.26
Sushi img with bg from website |  | Incase if we have any other images with the bg like this from the shoot kindly share that as well |  | High | Amar | 09.07.26 | 09.07.26 | Finish | Shared the file. | 2026-07-09
C4 Marinated Sleeves: |  | 1. barcode below the netweight 2. address to be changed to: THE DEEP SEAFOOD FACTORY LLC - in english and in arabic 3. Net weight - weight variation to be added +- 20gm |  | High | Amal | 09.07.26 | 09.07.26 | In Progress
Wet wipes |  | Regarding the wet wipes this is what purchasing team as provided us kindly suggest us the closest/similar shade for to proceed with bulk printing we can mix and match green and golden from the options provided |  | High | Amal | 09.07.26 | 10.07.26